## Taul1
RISK ANALYSIS - EXAMPLE
Elements | Risk | Consequence | Possibility | Severity | Steps to avoid, or at least minimize the risk
Crowd | Large number of people arriving or departing simultaneously | Suspending the event, person injuries, accidents, damages to infrastructure, reputation |  |  | The maximum capacity of attendance is specified in advance and access to the area is restricted in advance with e.g. fences, and barriers.
| Too many people allowed to entry the event area |  |  |  | The event area is planned to serve the maximum number of people, adequate amount the free space is reserved, and temporary structures of the event are properly located
| People crammed e.g. in front of the event stage |  |  |  | Entry routes and exit routes are properly designed and clearly marked. Queuing arrangements are organised appropriately
| Inadequate exit routes |  |  |  | Design of schedules and event programme in a way that no jams can occur
| Poor event area planning |  |  |  | Provide sufficient number of security staff and professsional security guards
| Aggressive people |  |  |  | Training of staff for preventing crowd
| Lack of guidance and information for the public |  |  |  | Continous monitoring of the public in the event area, and address problems in advance
Provide comprehensive sound system and megaphones to guide the public
Disruptive behaviour | Aggressive or intoxicated person | Suspending the event, person injuries, accidents, damages to infrastructure, reputation |  |  | Provide sufficient number of security staff and professsional security guards
| Poor arrangements of the event, e.g. queuing, poor event area planning |  |  |  | Provide training for the staff on how to handle disruptive behavior and situations
| Disappointment |  |  |  | Security checks at the entries to remove prohibited articles and substances
| Demonstration |  |  |  | Continous monitoring at the event area
Comply with and enforce alcohol legislation
Fire | Defective electrical equipment | Suspending the event, person injuries, accidents, damages to infrastructure, reputation |  |  | Comply with and enforce laws and legislations
Provide adequate initial fire-fighting and extinguishing equipment by fire brigades
Keep exit routes accessible, rescue routes unobstructed
| Smoking |  |  |  | Prohibit smoking , or at least show designated smoking areas. Containers made of non-combustible material.
| Violence |  |  |  | Communicate and prepare fire safety arrangements with the Fire Department and other authorities
| Pyrotechnic |  |  |  | Check all electrical equipment and installations before commissioning, and defective and dusty equipment will be deactivated
| Fireworks |  |  |  | Ensure there is no combustible material near the Food & Beverages preparation areas, ensure adequate distance
| Open fire |  |  |  | Fire safety of furnishing and decorations
| LPG |  |  |  | Continuous monitoring in the event area
| Combustible liquids |  |  |  | Training of staff to prevent and operate in fire incidents
Prepare a declaration of pyrotechnic / fire performance / fireworks according to national laws and legislations, with the relevant security arrangements being followed
Weather | Exceptionally warm or cold weather; hard wind; storm; heavy rain; thunderstorm, lightning, | Suspending (or temporary suspending) the event, cancel or postpone the event, person injuries, accidents, damages to infrastructure, reputation |  |  | Monitoring weather forecast before the event and, if necessary, cancelling the event
Guide the public to prepare for the weather
Continuously monitor the weather forecast, and try to respond at early stage
Secure temporary structure with appropriate weights
Check the condition of all temporary structures before the start of the event, and do regular checks during the event
A construction certificate is required for all temporary structures
Aware of the wind-limits for temporary structures and knowledge of procedures if the wind exceeds certain limits
Favor wind-permeating materials in material selection
Urge public and staff to drink enough water in case of hot weather, and provide enough water / drinking points for them
Instruct staff to work in different weather conditions
Accident / illness | Stumbling, falling, slipping, fall of a person, fall of an object, snow or ice fall, collapse of infrastructure, defective electical equipment, LPG, pyrotechnics, fire show, fireworks, traffic, disruptive behavior, weather conditions, crowd, food poisoning, | personal injuries, suspending (or temporary suspending) of the event, reputation |  |  | Provide tools for limiting and marking hazardous areas
Use of tools and materials to prevent slippery, e.g. sand
Provide adequate number of first-aid personnel and equipment
Provide enough water for the public and staff
Training of staff in case of emergencies and accident stituations
The bumpy and slippery floor / terrain / structures are monitored and fixed
Prevent public access to proximity to the use and storage location of liquefied petroleum gas and combustible liquids by means of fences or tapes
Pyrotechnic / fire / fireworks declaration needs to be issued with a declaration of compliance with the security arrangements
Traffic plan, sufficient amount of traffic officers allocated
Staff is trained to observe and report accidents and disturbances, and to intervene
Monitoring customers' condition and intervening
Ensure that food industry legislation is complied
Environmental | Poor waste management, lack of sustainable solutions, | Harmful effects to the surrounding areas, e.g. nature and waterfronts, reputation |  |  | Complying with the environmental laws and regulations
Organisation keeps records of hazardous waste, store them safely, and delivers the waste to the appropriate treatment.
Designated person/group responsible for environmental issues
Organisation has a waste management plan. Waste is sorted in accordance with the local waste management regulations, at the least.
Organisation makes an environmental review to identify the baseline of environmental issues management, and the organization’s major environmental impacts.
Organisation has an environmental policy
Marketing and partnerships | Withdrawal or inactivity of partners |  |  |  | Provide a variety of partner-levels and -activities.
Ambush marketing
| Misuse of the Olympic rings |  |  |  | Protection of the Olympic rings
Financial | Unrealistic budget, surprising costs |  |  |  | Carefully and thoroughly planned realistic budget
| Too high entry fees |  |  |  | Clear roles and responsibilities
Event makes a loss
Human resources
Lack of professional people and volunteers
Last minute cancellations
Information Management | Lack of information flow |  |  |  | Clear communication within the organisation
| Data corruption, loss of data |  |  |  | Changes in schedules need to be informed clearly
| Discrepansies in schedules |  |  |  | TIMETABLES, and their check-ups daily